## Community events
Checklist for a successful presentation - community events e.g. mosques, islamic organisations, women etc.
Before | Owner | Yes/No | On the day | Owner | Yes/No | Follow up | Owner | Yes/No
4 weeks before event |  |  | Register each attendee |  |  | Email each attendee within 24 hours
* Confirmation of official go-ahead for event, including venue. |  |  | * Set up table at entrance |  |  | Thank them for coming
2 weeks before event |  |  | * Try to register people via laptop with details going straight to Mend central |  |  | Let them know date / venue of next WG meeting
* Book accredited Causes & Cures presenter and support team (1-2) |  |  | * Imam (if mosque) to announce after salah to stay around for presentation
Tell them to tell others!
* Obtain marketing material from Mend HQ (Head of Divisions on Slack), tweek with details of event |  |  | Standing Orders
- Poster (PDF for printing out) |  |  | * Final few slides of presentation give most effective message to maximise SOs
- Telegram/Whatsapp image for social media marketing |  |  | * See if there is a way to electronically sign people up for SOs quickly and efficiently |  |  | Implement contact plan for database and invite relevant people to meetings and events
New Working Group members
* Market event |  |  | * Again, final few slides of presentation give most effective message to maximise recruitment of new WG members
- Mosque/centre noticeboard
- Jumma announcement |  |  | * Hand out Mend packs
- Local mailing lists
1 week
* Latest causes & cures presentation from Mend HQ (Head of Divisions on Slack)
* Latest handouts from Mend HQ
- Islamophobia brochures
- Standing order forms
- Action alert pocket guide
- Masterclass flyers
- Registration spreadsheet
* Ensure necessary equipment
- Laptop
- Projector
- Clicker
- Screen/wall availability
- Cater for ladies
- Extension wire
- Mend banner
* Venue checklist
- Microphone
- Speakers
- Table/chair for registration
A
B
C

## Bespoke events
Checklist for a successful Causes & Cures Presentation
Before | Owner | Tickbox | On the day | Owner | Tickbox | Follow up | Owner | Tickbox
3-6 months before event |  |  | Register each attendee |  |  | Email each attendee within 24 hours
* Send letter to venue introducing Mend and desire to host presentation |  |  | * Set up table at entrance |  |  | * Thank them for coming.
* Confirmation of official go-ahead for event, including venue. |  |  | * Try to register people via laptop with details going straight to Mend central
* Ensure sponsorship obtained where money needs to be spent |  |  | * Imam (if mosque) to announce after salah to stay around for presentation |  |  | * Let them know date / venue of next WG meeting (if applicable) Tell them to tell others!
2-4 weeks before event |  |  | Standing Orders
* Book accredited presenter and support team (1-2) |  |  | * Final few slides of presentation give most effective message to maximise fundraising |  |  | * Add attendee details to local database and send all details/forms to Amina Raouf at Mend HQ
* Obtain generic posters and whatsapp/Telegram images from Mend HQ (Head of Divisions on Slack), tweek with details of event |  |  | * See if there is a way to electronically sign people up for one-off donations quickly and efficiently
* Market event | [5 empty] | * Implement contact plan for database and invite relevant people to meetings and events
- Poster on mosque noticeboard, community centres, local businesses |  |  | New Working Group members (if appropriate)
- Jumma announcement
- Telegram/whatsapp messages sent out |  |  | * Again, final few slides of presentation give most effective message to maximise recruitment of new WG members
- Local mailing lists
- Call/email individuals if appropriate for personal invitations |  |  | * Hand out Mend packs
1 week
* Latest causes & cures presentation from Mend HQ (Head of Divisions on Slack)
* Latest premium handouts from Mend HQ
- Folder
- Islamophobia Exhibition Guides
- Annual report
- Manifesto
* Ensure necessary equipment
- Laptop
- Projector
- Clicker
- Screen/wall availability
- Cater for ladies
- Extension wire
- Mend banner
- Clipboards for collecting contact details
* Venue checklist
- Microphone
- Speakers
- Table/chair for registration
A
B
C
A
B
C